## Sheet1
Epworth RFP Pricing - 16 June 2025
Option | Submitted 5th June 2025: | 2625500
1 | Price Submitted - Original W'fall Plan | Rate | Days | Total | 58 weeks total
| Engagement Lead / Project Manager | 1800 | 290 | 522000
| Business Analyst | 1600 | 290 | 464000
| Cloud Architect | 1800 | 30 | 54000
| Data Architect | 1800 | 55 | 99000
| Senior Data Engineer | 1800 | 460 | 828000 |  |  | 6 resourcers
| Data Engineer | 1600 | 410 | 656000
| Hypercare | 1600 | 10 | 16000 | "Up to 2 months Hypercare" was presented, not just 2 weeks
| Contingency | 0 | 0 | 0
|  |  |  | 2625500 |  | No discount, rate card
2 | Price Updated - 14 Delivery Sprints | Rate | Days | Total | 48 weeks total
| Engagement Lead / Project Manager | 1800 | 240 | 432000 | 3 x intelia Snr Data Engineers + 3 x intelia Data Engineers
| Business Analyst | 1600 | 240 | 384000 | Iterative approach reduces effort from 58 weeks to 48,
| Cloud Architect | 1800 | 30 | 54000
| Data Architect | 1800 | 55 | 99000
| Senior Data Engineer | 1800 | 510 | 918000
| Data Engineer | 1600 | 420 | 672000
| Hypercare | 1600 | 10 | 16000
| Contingency | 0 | 0 | 0 |  | Saving from original proposal
|  |  |  | 2575000 |  | 50500
[8 empty] | 5% | 0.95
3 | Including 2 x Epworth DE's | Rate | Days | Total |  |  |  | Rate | Days | Total
| Engagement Lead / Project Manager | 1800 | 240 | 432000 | 48 weeks total |  |  | 1710 | 240 | 410400
| Business Analyst | 1600 | 240 | 384000 | 14 sprints | 3 x intelia Snr Data Engineers + 1 x intelia Data Engineer |  | 1520 | 240 | 364800 | ORIGINAL PRICE | 2625500 | % Reduction
| Cloud Architect | 1800 | 30 | 54000 | Using 2x their people for build phase - crawl walk run/shadow |  |  | 1710 | 30 | 51300 |  |  | of Original Price
| Data Architect | 1800 | 55 | 99000 |  |  |  | 1710 | 55 | 94050 | 54-44weeks | 2575000 | 1.961%
| Senior Data Engineer | 1800 | 510 | 918000 |  |  |  | 1710 | 510 | 872100
| Data Engineer | 1600 | 140 | 224000 |  |  |  | 1520 | 140 | 212800 | Remove 2 engineers | 2127000 | 18.99%
| Hypercare | 1600 | 10 | 16000 |  |  |  | 1520 | 10 | 15200
| Contingency | 0 | 0 | 0 |  | Saving from original proposal |  | 0 | 0 | 0 | 5% on our resources | 2020650 | 23.04%
|  |  |  | 2127000 |  | 498500 |  |  |  | 2020650
[11 empty] | 7.5% on our resources | 1967475 | 25.06%
[8 empty] | 7.5% | 0.925
4 | Role - Epworth DEs Update | Rate | Days | Total | What-if planning (remember - still fixed proce) |  |  | Rate | Days | Total | 10% on our resources | 1914300 | 27.09%
| Engagement Lead / Project Manager | 1800 | 120 | 216000 | All rates reduced |  |  | 1665 | 240 | 399600
| Business Analyst | 1600 | 120 | 192000 | PM + BA only "billed" out at 120 days each |  |  | 1480 | 240 | 355200 | 12.5% on our resources | 1861125 | 29.11%
| Cloud Architect | 1800 | 30 | 54000 | Using their people + halving PM and BA same out put |  |  | 1665 | 30 | 49950
| Data Architect | 1800 | 55 | 99000 |  |  |  | 1665 | 55 | 91575 | 15% on our resources | 1807950 | 31.14%
| Senior Data Engineer | 1800 | 510 | 918000 |  |  |  | 1665 | 510 | 849150
| Data Engineer | 1600 | 140 | 224000 |  |  |  | 1480 | 140 | 207200
| Hypercare | 1600 | 10 | 16000 |  |  |  | 1480 | 10 | 14800
| Contingency | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 1719000 | [5 empty] | 1967475
| Saving | + Google Cloud Skills Lic | Google credit |  |  |  |  | 10% | 0.9
| 906500 | 59800 | 500 | 966800 |  |  |  | Rate | Days | Total
| Epworth resources we can leverage to reduce our price: 2 x data engineers. Any other resource will simply "bolster" our team, not replace | [6 empty] | 1620 | 240 | 388800
| Should Epworth wish to manage the project themselves (ie: remove intelia PM) this could be considered however we cannot offer fixed price as they then take accountability for delivery, not intelia (we could offer them resource augmentation T&M instead) | [6 empty] | 1440 | 240 | 345600
| 100 x Google Cloud Skills Boost licenses, for 24 months = $59,800 | [6 empty] | 1620 | 30 | 48600
| $500 google consumption credit | [6 empty] | 1620 | 55 | 89100
[8 empty] | 1620 | 510 | 826200
[8 empty] | 1440 | 140 | 201600
[8 empty] | 1440 | 10 | 14400
[8 empty] | 0 | 0 | 0
1914300
[8 empty] | 12.5% | 0.875
[8 empty] | Rate | Days | Total
[8 empty] | 1575 | 240 | 378000
[8 empty] | 1400 | 240 | 336000
[8 empty] | 1575 | 30 | 47250
[8 empty] | 1575 | 55 | 86625
[8 empty] | 1575 | 510 | 803250
[8 empty] | 1400 | 140 | 196000
[8 empty] | 1400 | 10 | 14000
[8 empty] | 0 | 0 | 0
1861125
[8 empty] | 15% | 0.85
[8 empty] | Rate | Days | Total
[8 empty] | 1530 | 240 | 367200
[8 empty] | 1360 | 240 | 326400
[8 empty] | 1530 | 30 | 45900
[8 empty] | 1530 | 55 | 84150
[8 empty] | 1530 | 510 | 780300
[8 empty] | 1360 | 140 | 190400
[8 empty] | 1360 | 10 | 13600
[8 empty] | 0 | 0 | 0
1807950