## Slide 1: High-level Plan: Main Phases and Outcomes
intelia.ai
DISCOVERY &
PLANNING
ESTABLISH
PLATFORM
BUILD, MIGRATE,
TEST, DEPLOY
TRANSITION
& HYPERCARE
PROJECT
CLOSURE
Project kick off
Capture detailed requirements
Comprehensive solution architecture
Detailed project plan
8 Weeks
6 Weeks
28 Weeks
2 - 8 Weeks
Provision Google Cloud platform
Establish secure connectivity into Epworth environment
Provision Development, UAT, and Production environments
14 x 2 week Sprints (agreed backlog order)
Migrate data source(s) + SSIS packages etc
Reconstruct and present Interface Layer models
Testing & Validation
Documentation
Iterative Production Deployment
Deliver technical handover documentation
Conduct handover sessions for Epworth IT team
Host training workshops for business users
Provide up to 2 months Hypercare
Final project status / update meeting
Agree next steps
Formally agree to close project
Project Management and Status Reporting

## Slide 2: High-level Plan: Gantt Chart View
intelia.ai
Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14
2025 |  |  |  |  |  | 2026 |  |  |  |  |  |  | 
JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
Discovery & Planning
Establish
Platform
Build, Migrate, Test, Deploy
Transition &
Hypercare
8 weeks
6 weeks
28 weeks (14 x 2 week sprints delivering iterative value drops into Production)
Up to 8 weeks
Project kick off
Capture detailed requirements
Comprehensive solution architecture
Project timeline
Provision GCP
Establish connectivity
Provision DEV, TEST & PROD
Handover sessions
Training w’shops
Up to 2 months Hypercare
Project
Close
Iterative releases based on agreed prioritised backlog
SSIS (and other) packages will be refactored to ingest source data into the platform
Interface Layer models will be reconstructed
Testing & Validation will be completed, along with appropriate documentation
Each drop into Production will enable Power BI dashboards to be connected into the new Interface Layer ensuring Epworth can realise value throughout the project’s life cycle
Note: July 2025 commencement indicative only